## Sheet1
Task ID | Task Name | Description | Owner | Estimated Time
T-001 | Set Up Python Environment | Install Python, pip, virtualenv, and set up a clean dev environment. | Dev Team | 2h
T-002 | Explore Codebase | Review all classes/functions in the validator. List what each part does. | Dev Team | 3h
T-003 | Document Functions | Add inline comments explaining each function in plain English. | Dev Team | 3h
T-004 | Run Script with Sample Feeds | Load small CSV/JSON feeds and run the validator to see how it works. | Dev Team | 2h
T-005 | Create Sample Feed Files | Build valid/invalid feed files for GPUs, AI chips, etc. | Dev Team | 2h
T-006 | Export Cleaned Feed to JSON | After validation, save cleaned entries in structured JSON format. | Data Eng. Team | 3h
T-007 | Export Invalid Rows Separately | Save entries with errors in a separate file for manual review. | Data Eng. Team | 2h
T-008 | Normalize Units | Convert all units (GB, GHz, W) to a standardized format (e.g., 32 GB). | Data Eng. Team | 3h
T-009 | Flatten Nested Specifications | Ensure specs in dict format are flattened or consistently structured. | Data Eng. Team | 3h
T-010 | Fetch API Contract from Backend | Get exact schema of Spring Boot API for product ingestion. | Data Eng. Team | 1h
T-011 | Map Validator Output to API Format | Ensure exported JSON matches Spring Boot product schema. | Data Eng. Team | 2h
T-012 | Add API POST Logic in Python | Use requests.post() to send cleaned data to /api/products/import. | Data Eng. Team | 3h
T-013 | Add API Error Handling | Log and retry failed HTTP requests with error context. | Data Eng. Team | 2h
T-014 | Include Feed Metadata in Payload | Add timestamp, uploader, and file info to the payload sent to backend. | Data Eng. Team | 2h
T-015 | Use Chunked Uploads | Send feed data in 100-record batches to avoid timeouts. | Data Eng. Team | 3h
T-016 | Add CLI Flag to Skip Upload | Add a --no-upload option to only export data without posting. | Data Eng. Team | 1h
T-017 | Fetch Categories via API | Load valid categories dynamically from /api/categories. | Data Eng. Team | 2h
T-018 | Add Retry Logic for Uploads | Add retries with backoff for failed POSTs due to backend issues. | Data Eng. Team | 2h
T-019 | Read Feed from S3 | Enable validator to fetch feed files from S3 using boto3. | Data Eng. Team | 4h
T-020 | Track Upload Metadata | Save metadata (filename, uploader, count) locally or post to API. | Data Eng. Team | 2h
T-021 | Generate Validation Summary Report | Write a Markdown/JSON report for each run showing errors, counts. | Data Eng. Team | 2h
T-022 | Create Feed QA Jupyter Notebook | Use pandas to profile feed content, outliers, missing data, etc. | Data Eng. Team | 4h
T-023 | Create Visualization of Errors | Bar chart of most common field errors (optional in Jupyter). | Data Eng. Team | 2h
T-024 | Collaborate with Spring Boot Team | Confirm API behavior and schema with backend developers. | Data Eng. Team | 2h
T-025 | Track Feed Upload History via API | Ensure validator sends summary data to a feed-logs endpoint. | Data Eng. Team | 2h
T-026 | Confirm Where Specs Go | Align with backend: are specifications stored in MySQL or MongoDB? | Data Eng. Team | 1h
T-027 | Build File Upload UI in React | Simple admin page for uploading product feed file. | Frontend Dev | 4h
T-028 | Display Upload Summary in UI | After upload, show success/failure stats (products passed, failed). | Frontend Dev | 3h
T-029 | Add Upload History Table | Display all feed uploads, with links to reports and data. | Frontend Dev | 4h
T-030 | Dockerize the Validator | Add Dockerfile to containerize the validator script. | DevOps | 3h
T-031 | Add Jenkins Job for Validator | Run validation as part of Jenkins CI pipeline for staging feeds. | DevOps | 4h
T-032 | Schedule Daily Validation Job | Use cron, Jenkins, or Lambda to auto-run validator daily. | DevOps | 3h
T-033 | Add pydantic Validation Layer | Use pydantic for stricter field rules and automatic type checks. | Dev Team | 4h
T-034 | Add Dry Run Mode | Run validator without writing or uploading anything – just report. | Dev Team | 1h
T-035 | Tag Each Product with Feed ID | Add a feed_id to each product record for traceability. | Data Eng. Team | 1h
T-036 | Save Clean Feed for AI Use | Save validated feed to an S3 bucket for AI model training. | Data Eng. Team | 2h
T-037 | Notify AI Team of New Feed | Automate a webhook, file flag, or Slack message when new clean feed is available. | Data Eng. Team | 1h
T-038 | Write Dev Guide (Markdown) | Step-by-step guide for running, editing, and testing the validator. | Dev Team | 2h
T-039 | Write Feed Format Spec | Document what a valid feed should look like (field names, types, examples). | Dev Team | 2h
T-040 | Create Team Training Slides | Present basic validator concepts, how to contribute, and test. | Lead Dev | 2h
T-041 | Host Validator Walkthrough Session | 30-60 min session for training the team on how it works. | Lead Dev | 1h